## Project Checklist
Yantriksha X Hub: Website Complete Project Checklist
Task ID | Phase / Category | Task Name | Detailed Requirement Specification | Completed
INF-01 | 1. Infrastructure | Git Setup | Initialize empty Git repository in root folder. | Completed
INF-02 | 1. Infrastructure | Repository Backup | Backup NITTTR Internship files to a local backup folder (.git_nitttr_backup). | Completed
INF-03 | 1. Infrastructure | Gitignore Config | Excludes private credentials (.env) and testing logs (test-connection.js) from remote pushes. | Completed
INF-04 | 1. Infrastructure | Skeleton Setup | Create package.json, clean-url vercel.json, and public/api folder layouts. | Completed
INF-05 | 1. Infrastructure | Dependency Resolving | Run npm install to locally download mysql2, vercel CLI, and dotenv libraries. | Completed
DB-01 | 2. Database | TiDB Cluster Setup | Provision TiDB Serverless instance 'vignesh' on AWS Singapore region. | Completed
DB-02 | 2. Database | Traffic Filter Config | Whitelist '0.0.0.0/0' in TiDB console under Security settings to allow Vercel dynamic IPs. | Completed
DB-03 | 2. Database | Connection Verify | Ensure test-connection.js executes successfully showing DB timestamp locally. | Completed
DB-04 | 2. Database | User Schema | Create SQL table 'users' containing roles (Eng/Law/MBA), emails, and student IDs. | Completed
DB-05 | 2. Database | Team Schema | Create SQL tables 'teams' and 'team_members' mapping cross-disciplinary allocations. | Completed
DB-06 | 2. Database | Report Schema | Create SQL table 'progress_reports' to store bi-weekly milestone report references. | Completed
DB-07 | 2. Database | Funding Schema | Create SQL table 'funding_requests' to track the ₹50,000 seed budget items and approvals. | Completed
DB-08 | 2. Database | Scheduler Schema | Create SQL table 'bookings' to coordinate weekly mentorship slots. | Completed
DB-09 | 2. Database | Podcast Schema | Create SQL table 'podcast_qa' to record audience submitted questions. | Completed
API-01 | 3. Backend API | DB Wrapper Hook | Establish secure connection pool with SSL/TLS rejectUnauthorized in api/db.js. | Completed
API-02 | 3. Backend API | Test DB Endpoint | Develop serverless function api/test-db.js returning test calculation and time. | Completed
API-03 | 3. Backend API | Authentication APIs | Create registration and login APIs with JWT tokens blocking external domains. | Completed
API-04 | 3. Backend API | Team Matching APIs | Develop APIs to query unassigned users, create teams, and manage invites. | Completed
API-05 | 3. Backend API | Milestone Progress APIs | Develop APIs to retrieve roadmap status, submit reports, and post mentor reviews. | Completed
API-06 | 3. Backend API | Funding Requests APIs | Develop budget creation, listing, and updates endpoints for Treasurer/Advisors. | Completed
API-07 | 3. Backend API | Podcast Q&A APIs | Develop public question submissions and admin review endpoints. | Completed
UI-01 | 4. Frontend UI | HTML Skeleton Layout | Construct public/index.html layout, navbar anchors, leadership grids, and footers. | Completed
UI-02 | 4. Frontend UI | Design Theming & Layouts | Code public/style.css design variables, glassmorphic styles, and grid responsiveness. | Completed
UI-03 | 4. Frontend UI | App Interactivity scripts | Code public/app.js tab events, modal timeline info panels, and indicator fetches. | Completed
UI-04 | 4. Frontend UI | Phase Swapper Tab | JavaScript toggle to switch stage details (-1 Confusion, 0 Idea, 1 Product). | Completed
UI-05 | 4. Frontend UI | 14-Stage Roadmap Modals | JavaScript hook to open detail popups for each of the 14 timeline cards. | Completed
UI-06 | 4. Frontend UI | Compliance Team Builder | Interactive calculator updating compliance percentage based on member disciplines. | Completed
SEC-01 | 5. Security | IP whitelisting rules | Limit direct DB access to approved traffic filters. | Completed
SEC-02 | 5. Security | Route Guards | Implement backend validation middleware verifying JWT tokens before serving records. | Completed
SEC-03 | 5. Security | Confidentiality gate | Require explicit Code of Conduct agreement before unlocking matchmaking tools. | Completed
DEP-01 | 6. Deployment | Vercel Dev check | Confirm npx vercel dev compiles and runs frontend assets and local API routes. | Completed
DEP-02 | 6. Deployment | Link Repo to Vercel | Import personale88/Yantriksha-X-Hub into Vercel dashboard. | Completed
DEP-03 | 6. Deployment | Environment Config | Define env variables (TIDB_HOST, etc.) securely inside the Vercel dashboard. | Completed
DEP-04 | 6. Deployment | Staging Rollout | Deploy staging branch, perform DB connectivity checks, and audit speeds. | Completed
DEP-05 | 6. Deployment | Domain Mapping | Map custom domain (yantriksha.veltech.edu.in) to Vercel production server. | Completed
DEP-06 | 6. Deployment | Production Launch | Merge staging to main to trigger production deploy compile. | Completed